INTERNATIONAL TRAVEL RISK TEMPLATE

We have provided an illustrative template to fill out as necessary; please note the examples listed below are only examples – you are responsible for identifying and mitigating all risks associated with your activity. Please add other potential risk areas to the template as appropriate to your activity.

Name: Joel Sarakula

Organisation: Joel Sarakula

| What are the risks? | Who might be impacted and how? | What is the impact of this risk? (Mild/Moderate/Severe) | What is the likelihood of this risk? (Low/Medium/High) | What are you doing to manage and/or mitigate this risk? | Action by whom? | Action by when? | Done |
| --- | --- | --- | --- | --- | --- | --- | --- |
| International border or flight issues before or during my activity | Only myself for my flights between UK and the EU My touring bands are local to my tour starting points of Barcelona and Berlin. Please note: the tours will cross EU national borders (Spain – France and Germany – NL – Austria) but because of the schengen agreement, there are NO border controls in place between these countries. Mainland EU is essentially one secured border-less zone within itself, similar to Australia. | Mild | Low. Please note: UK – EU flights are considered a kind of domestic flights in Europe, serviced by many budget airlines. They are regularly travelled and serviced routes. There are only ever a very small number of cancelled flights, even less in an off-peak month like November. Flights are mainly cancelled due to industrial action or adverse weather. | - I will arrive THREE days before the start of each show. Aside from leaving time for rehearsals and in-studios, this also leaves a large buffer zone in the extremely unlikely case of cancelled flights due to industrial action or adverse weather. - I will follow any potential industrial action / adverse weather a week or so before the tour. In the unlikely event that my flights may be affected by adverse weather or industrial action, I can take action and book a new flight, eg. to arrive a day or two before. I live in the UK. Flying to Germany or Spain is like flying from SYD – MEL. I will have comprehensive travel insurance in place too in case I need to book new flights. Please note I have an AUS and UK passport and a Spanish working visa allowing me full, unquestioned access to UK/EU. | Myself |  |  |

You should continue to review your risk assessment leading up to and during your activity to ensure it remains current and appropriate or if you think it might no longer be valid or if there are any significant changes to your project or activity.